## Sheet1
SEVERITY
| Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level |  |  | Minimal | Minor | Moderate | Major | Severe
1 | Database is attacked by an attacker | If a database is attacked by a bad actor, this will make the database's contents comprimised. The attacker may use something like an SQL injection and the data will be breached. Although the data on this website isn't inherently dangerous - unless they are using the same usernames and passwords across multiple accounts. | make sure the database is initially secure | to restore service as soon as possible | medium | Minimal | 2 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
2 | Database stops working | If the database hosted in GCP or H2 goes down the website will go down and be non-functional.We will not be able to do any CRUD requsts. | check the issues and switch it to a running instance as soon as possible | to restore service to the database as soon as possible | low | minimal | 2 |  | Expected | 4 | 8 | 12 | 16 | 20
3 | Web Server Stops working | If the web server hosted in GCP goes down the website will go down and be non-functional. | see if you can re route the traffic to another server | ensure as much uptime as possible | low | minimal | 2 |  | Likely | 3 | 6 | 9 | 12 | 15
4 | Database is deleted by an attacker | If the database is deleted, the application will become unusable. In this case, it would not cause immediate risk to the users as the details that are stored in this application are only integral to the application itself, and it therefore has a minimal risk. | if there is no backup there is not much we can do | if no backup - ensure as much data can be recreated as possible in as short a time as possible | low | high | 6 |  | Possible | 2 | 4 | 6 | 8 | 10
5 | Attacker initiates DDOS attack | If a DDOS attack is initiated, it will bring the website down. There is no inherent danger in leaking any usernames / password stored on the database here but the website would defiintely go down. The website is only a test case for a project so the likeihood of reciveing a DDOS attack is minimal to nil. | restart the application on a different server privately | to block the malicius ip/ips attacking the server | low | high | 1 |  | Unlikely | 1 | 2 | 3 | 4 | 5
6
7